## Sheet1
Risk Identification |  | Qualitative Rating |  |  |  | Risk Response
Risk | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger | Risk Owner
Hardware malfunction or failure | Technical | Low | Low | 4 | Low | Regular maintenance, backup equipment, and training for staff | Equipment downtime or errors | Project Manager
Insufficient funding or budget overruns | Financial | Low | Medium | 6 | Medium | Regular budget monitoring, cost control measures, and contingency planning | Cost overruns or funding cuts | Project Manager
Delays in project implementation due to unforeseen issues | Schedule | Medium | High | 12 | High | Project schedule monitoring, contingency planning, and proactive issue resolution | Project delays or missed deadlines | Project Manager
Integration challenges with AI tools | Technical | Medium | High | 12 | High | Detailed technical assessments, collaboration with vendors, and contingency plans | Compatibility issues or data integration problems | Project Manager
Low customer adoption rates | Market | Medium | High | 10 | High | Market research, user feedback mechanisms, and iterative product development | Negative customer feedback or declining sales | Marketing Manager
Limited availability of skilled workforce, technology resources | Resource | High | High | 15 | High | Resource optimization strategies, workforce development initiatives | Shortage of skilled personnel or insufficient technology resources | Project Manager
Total dependency on third-party vendor for AI tools | External Dependency | High | Medium | 12 | High | Negotiate robust service level agreements with the vendor, ensuring clear expectations for performance, reliability, and support | Vendor service disruptions or contractual breaches | Project Manager
Non-compliance with industry regulations, data privacy laws, or licensing requirements | Legal/Compliance | Medium | High | 8 | Medium | Legal compliance audits, implementation of robust data security measures, and ongoing regulatory monitoring | Regulatory changes or audits | Legal Counsel
Scope creep due to changes in project scope, requirements, or stakeholder expectations | Scope | High | Medium | 12 | High | Formal change control processes, stakeholder engagement, and comprehensive impact assessments | Change requests or evolving stakeholder needs | Project Manager
Competitive pressure from rapid advancements in AI technology and rival companies | Market | Medium | High | 12 | High | Continuous market analysis, product differentiation strategies, and agile response to market changes | Emergence of new competitive products or technologies | Marketing Manager
Resistance to change or lack of user training and support | Organizational | Medium | Medium | 6 | Medium | Comprehensive training programs, change management initiatives, and user support channels | Employee pushback or lack of user engagement | Change Management Lead
Key Terms
Risk: The risk stated in a complete sentence which states the cause of the risk, the risk, and the effect that the risk causes to the project.
Risk Category: Categorization of risks by area of project affected, source of risk or other useful category.
Probability: The likelihood that a risk or opportunity will occur (on a scale from 0 to 10 with 10 being the highest).
Impact: The impact of the risk on the project if the risk occurs (scale from 0 to 10 with 10 being the highest).
Risk Score: Determined by multiplying probability and impact (scale from 0 to 100).
Risk Ranking: A priority list which is determined by the relative ranking of the risks (by their scores) within the project with the number one being the highest risk score.
Risk Response: The action which is to be taken if this risk occurs.
Trigger: Something which indicates that a risk is about to occur or has already occured.
Risk Owner: The person who the project manager assigns to watch for triggers, and manage the risk response if the risk occurs.
This Risk Register Template is brought to you by www.projectmanagementdocs.com