## TRACK MY TASKS
Clayton DeSimone, Project Management, Assignment 14, 3/25/2024
Task Tracking Template
Project Name Here
Task Name/ Description | Dependent Tasks | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Status | Notes
Project Initiation |  | Clayton DeSimone | Low | 2024-01-01 08:00 | 2024-01-31 17:00 | 2024-02-15 | CLOSED | Objectives are defined, stakeholders are identified, the project charter is developed, approval for the project charter is obtained, and a kickoff meeting is conducted.
Requirement Analysis | Project Initiation | Jane Smith | High | 2024-02-01 08:00 | 2024-03-31 17:00 | 2024-04-10 | CLOSED | User requirements are gathered, analyzed, documented, and transformed into functional requirements for the data analytics platform.
Design & Planning | Requirement Analysis | Rob Davis | High | 2024-04-01 08:00 | 2024-06-30 17:00 | 2024-07-05 | CLOSED | System architecture is designed, detailed design specifications are developed, project plans are defined, resources are allocated, and a risk management plan is established.
Prototyping | Design & Planning | Emily Brown | Critical | 2024-07-01 08:00 | 2024-07-31 17:00 | 2024-08-02 | CLOSED | A prototype of the data analytics platform is built, tested, and refined based on user feedback.
Frontend Development | Prototyping | Michael Green | High | 2024-08-01 08:00 | 2024-11-30 17:00 | 2024-12-10 | CLOSED | User interface of the data analytics platform is designed, developed, and tested.
Backend Development | Prototyping | Sarah Thomson | High | 2024-08-01 08:00 | 2024-11-30 17:00 | 2024-11-30 | CLOSED | Backend logic, database schema, and data integration processes of the data analytics platform are designed, implemented, and tested.
Integration & Testing | Backend Development | James Arnold | High | 2024-12-01 08:00 | 2025-02-28 17:00 | 2025-03-05 | CLOSED | Frontend and backend systems are integrated, and comprehensive testing is conducted to validate the platform's functionality and performance.
User Acceptance Testing | Integration & Testing | James Arnold | High | 2025-03-01 08:00 | 2025-03-31 17:00 | 2025-04-10 | CLOSED | Data analytics platform is tested by end-users to ensure it meets their requirements and expectations.
Bug Fixing & Refinement | Integration & Testing | Lisa White | High | 2025-03-01 08:00 | 2025-04-30 17:00 | 2025-06-05 | CLOSED | Identified bugs and issues are addressed, and the platform is refined based on user feedback.
Documentation | Bug Fixing & Refinement | Chris Taylor | Medium | 2025-05-01 08:00 | 2025-05-31 17:00 | 2025-06-05 | CLOSED | User manuals, technical documentation, and installation guides for the data analytics platform are created.
Training and Knowledge Transfer | Documentation | Alice Clark | Medium | 2025-06-01 08:00 | 2025-07-31 17:00 | 2025-08-05 | CLOSED | Training materials are developed, user training sessions are conducted, and knowledge is transferred to the support team.
Deployment | Training and Knowledge Transfer | Olivia Reynolds | Critical | 2025-08-01 08:00 | 2025-08-31 17:00 | 2025-09-02 | CLOSED | Data analytics platform is deployed into the production environment following a well-defined deployment strategy.
Post-Deployment Support | Deployment | Mark Pattenson | High | 2025-09-01 08:00 | 2025-11-30 17:00 | 2026-01-10 | CLOSED | User support is provided, post-deployment issues are addressed, and system performance is monitored.
Monitoring and Optimization | Deployment | Daniel Ray | Medium | 2025-09-01 08:00 | 2026-02-28 17:00 | 2026-01-31 | CLOSED | System usage is monitored, optimization opportunities are identified, and performance improvements are implemented.
Project Closure | Monitoring and Optimization | Grace Allen | Medium | 2026-03-01 08:00 | 2026-03-31 17:00 | 2026-05-15 | CLOSED | The project is formally closed out, project documentation is archived, resources are released, and project success is celebrated.
To add another row to your list, click the "insert" button in the top right, and then click "insert table row below."

## How to Use this Template
Introduction
Use this template to track your tasks. As a team member, or a manager, it's critical to take care of your daily work so the team can remain productive as a whole. Of course, you can use this template to track your tasks at home too!
Definition of Terms
MY TASKS: Enter the name of the task you need to do.
ASSIGNED TO: Enter the name of the person responsible for this task
PRIORITY: Enter low, medium, high, or critical
START DATE: Enter the date you need to start the task.
PLANNED END DATE: this is the intended due date
ACTUAL END DATE: Enter the date the task actually finished
Notes: Add any notes for context that you need.
To add another row to your list, click the "insert" button in the top right, and then click "insert table row below"