## Lessons Learned Template
Lessons Learned Template
Today's Date: | 2024-04-09
Project Name: | New Solutions Enterprise New Product Launch
Project Manager: | Clayton DeSimone
Notes:
WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
WIN | Successfully implemented automated deployment process for NSE project, reducing deployment time by 50%. | This led to improved efficiency and faster delivery of software updates. | In future projects, automated deployment processes will be prioritized to streamline development workflows. | 1. Document the automated deployment process for future reference. 2. Conduct training sessions for team members on the new deployment process.
ISSUE | Key developer left the project unexpectedly, causing a delay in the development phase. | Project timeline was extended by 1 weeks, impacting delivery deadlines and increasing project costs. | In future projects, implement knowledge transfer and maintain detailed documentation to handle risks associated with team turnover. | 1. Conduct a knowledge transfer session with remaining team members. 2. Review project documentation to ensure it is up-to-date and comprehensive.
WIN | Successfully integrated new AI module into the NSE platform, enhancing its capabilities and performance. | Client satisfaction increased, leading to positive feedback and potential for future collaborations. | Integration of advanced AI technologies should be explored in future projects to increase product offerings and attract more clients. | 1. Document the integration process for future reference. 2. Evaluate potential AI technologies for future projects.

## How to Use This Template
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in your project to repeat the positive and avoid the negative.
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve